## Executive Summary
Source workbook file | sample-smartsheet-schedule-input.xlsx
Worksheet used | Sample Schedule Export
Analysis generated timestamp | 6/2/2026, 1:16:29 PM
Total normalized rows | 20
Detail rows | 16
Likely parent/summary rows | 4
Rows with date warnings | 0
Rows excluded from movement calculations | 0
Rows with any schedule movement | 18
Unchanged rows | 2
Delayed rows | 12
Accelerated rows | 3
Start-only movement rows | 3
Rows with predecessor values | 14
Total predecessor references parsed | 14
Resolved predecessor links | 14
Unresolved predecessor links | 0
Rows with dependency warnings | 0
Project grouping column mapped | Yes
Number of project groups analyzed | 2
Latest current estimated project finish across project groups | 02/18/2026
Eligible critical path rows considered | 16
Rows excluded as likely parent/summary rows | 4
Baseline critical path task count | 16
Current critical path task count | 16
Baseline estimated project finish | 02/17/2026
Current estimated project finish | 02/18/2026
Estimated critical path finish shift | Not calculated
Tasks on both baseline and current path | 16
Tasks newly on current path | 0
Tasks no longer on current path | 0
Critical path calculation warnings | None
Largest finish delay | 2 workdays (4 calendar days) - Order finish materials
Largest finish acceleration | 0 workdays (-1 calendar days) - Remove existing finishes
Note | Parent/summary rows are excluded from estimated critical path analysis when hierarchy data or fallback heuristics identify them.
Note | When a Project Name / Project Grouping column is mapped, estimated critical paths are calculated separately for each project group.
Note | The analyzer works best when a Row Hierarchy / Outline Level helper column is mapped.
Note | Estimated critical path logic does not yet apply project-specific holiday calendars.
Note | This is not a full replacement for Smartsheet, P6, or MS Project CPM calculations.

## Changed Schedule Items
Project Name | Task ID | Task / Milestone | Row Classification | Hierarchy Level | Has Child Rows | Critical Path Eligible | Critical Path Exclusion Reason | Baseline Start | Current Start | Start Calendar Movement | Start Workday Movement | Baseline Finish | Current Finish | Finish Calendar Movement | Finish Workday Movement | Movement Status | Predecessors | Status / % Complete | Warnings | Excluded From Future Critical Path
Sample Lobby Refresh | LOB-000 | Sample Lobby Refresh Summary | likely-summary | 1 | Yes | No | Parent/summary row based on hierarchy | 01/06/2026 | 01/06/2026 | 0 | 0 | 01/29/2026 | 01/30/2026 | 1 | 1 | Delayed |  |  |  | Yes
Sample Lobby Refresh | LOB-020 | Order finish materials | detail | 2 | No | Yes | Eligible | 01/07/2026 | 01/08/2026 | 1 | 1 | 01/09/2026 | 01/13/2026 | 4 | 2 | Delayed | 2 |  |  | No
Sample Lobby Refresh | LOB-030 | Install temporary protection | detail | 2 | No | Yes | Eligible | 01/10/2026 | 01/13/2026 | 3 | 1 | 01/12/2026 | 01/14/2026 | 2 | 2 | Delayed | 3FS |  |  | No
Sample Lobby Refresh | LOB-040 | Remove existing finishes | detail | 2 | No | Yes | Eligible | 01/13/2026 | 01/14/2026 | 1 | 1 | 01/17/2026 | 01/16/2026 | -1 | 0 | Mixed Movement | 4FS+2d |  |  | No
Sample Lobby Refresh | LOB-050 | Wall prep and paint | detail | 2 | No | Yes | Eligible | 01/18/2026 | 01/17/2026 | -1 | 1 | 01/22/2026 | 01/22/2026 | 0 | 0 | Start Accelerated / Finish Unchanged | 5SS |  |  | No
Sample Lobby Refresh | LOB-060 | Lighting refresh package | likely-summary | 2 | Yes | No | Parent/summary row based on hierarchy | 01/23/2026 | 01/24/2026 | 1 | 0 | 01/28/2026 | 01/30/2026 | 2 | 2 | Delayed |  |  |  | Yes
Sample Lobby Refresh | LOB-070 | Remove old fixtures | detail | 3 | No | Yes | Eligible | 01/23/2026 | 01/24/2026 | 1 | 0 | 01/24/2026 | 01/25/2026 | 1 | -1 | Delayed | 6FS |  |  | No
Sample Lobby Refresh | LOB-080 | Install new fixtures | detail | 3 | No | Yes | Eligible | 01/25/2026 | 01/24/2026 | -1 | 1 | 01/27/2026 | 01/26/2026 | -1 | -1 | Accelerated | 8FS |  |  | No
Sample Lobby Refresh | LOB-090 | Final walkthrough | detail | 2 | No | Yes | Eligible | 01/28/2026 | 01/29/2026 | 1 | 1 | 01/29/2026 | 01/30/2026 | 1 | 1 | Delayed | 9FS |  |  | No
Sample Pool Repairs | POOL-000 | Sample Pool Repairs Summary | likely-summary | 1 | Yes | No | Parent/summary row based on hierarchy | 02/02/2026 | 02/02/2026 | 0 | 0 | 02/17/2026 | 02/18/2026 | 1 | 1 | Delayed |  |  |  | Yes
Sample Pool Repairs | POOL-020 | Drain and clean pool | detail | 2 | No | Yes | Eligible | 02/03/2026 | 02/03/2026 | 0 | 0 | 02/04/2026 | 02/05/2026 | 1 | 1 | Delayed | 12 |  |  | No
Sample Pool Repairs | POOL-030 | Surface inspection | detail | 2 | No | Yes | Eligible | 02/05/2026 | 02/06/2026 | 1 | 1 | 02/05/2026 | 02/06/2026 | 1 | 1 | Delayed | 13FS |  |  | No
Sample Pool Repairs | POOL-040 | Crack repair prep | detail | 2 | No | Yes | Eligible | 02/06/2026 | 02/07/2026 | 1 | 0 | 02/08/2026 | 02/08/2026 | 0 | 0 | Start Delayed / Finish Unchanged | 14FS+2d |  |  | No
Sample Pool Repairs | POOL-050 | Tile repair package | likely-summary | 2 | Yes | No | Parent/summary row based on hierarchy | 02/09/2026 | 02/08/2026 | -1 | 0 | 02/14/2026 | 02/14/2026 | 0 | 0 | Start Accelerated / Finish Unchanged |  |  |  | Yes
Sample Pool Repairs | POOL-060 | Remove damaged tile | detail | 3 | No | Yes | Eligible | 02/09/2026 | 02/08/2026 | -1 | 0 | 02/10/2026 | 02/09/2026 | -1 | -1 | Accelerated | 15SS |  |  | No
Sample Pool Repairs | POOL-070 | Install replacement tile | detail | 3 | No | Yes | Eligible | 02/11/2026 | 02/12/2026 | 1 | 1 | 02/13/2026 | 02/14/2026 | 1 | 0 | Delayed | 17FS |  |  | No
Sample Pool Repairs | POOL-080 | Deck coating touch-up | detail | 2 | No | Yes | Eligible | 02/14/2026 | 02/13/2026 | -1 | 0 | 02/16/2026 | 02/17/2026 | 1 | 1 | Mixed Movement | 18FS |  |  | No
Sample Pool Repairs | POOL-090 | Final inspection | detail | 2 | No | Yes | Eligible | 02/17/2026 | 02/18/2026 | 1 | 1 | 02/17/2026 | 02/18/2026 | 1 | 1 | Delayed | 19FS |  |  | No

## All Schedule Items
Project Name | Task ID | Task / Milestone | Row Classification | Hierarchy Level | Has Child Rows | Critical Path Eligible | Critical Path Exclusion Reason | Baseline Start | Current Start | Start Calendar Movement | Start Workday Movement | Baseline Finish | Current Finish | Finish Calendar Movement | Finish Workday Movement | Movement Status | Predecessors | Status / % Complete | Warnings | Excluded From Future Critical Path
Sample Lobby Refresh | LOB-000 | Sample Lobby Refresh Summary | likely-summary | 1 | Yes | No | Parent/summary row based on hierarchy | 01/06/2026 | 01/06/2026 | 0 | 0 | 01/29/2026 | 01/30/2026 | 1 | 1 | Delayed |  |  |  | Yes
Sample Lobby Refresh | LOB-010 | Kickoff and site review | detail | 2 | No | Yes | Eligible | 01/06/2026 | 01/06/2026 | 0 | 0 | 01/06/2026 | 01/06/2026 | 0 | 0 | Unchanged |  |  |  | No
Sample Lobby Refresh | LOB-020 | Order finish materials | detail | 2 | No | Yes | Eligible | 01/07/2026 | 01/08/2026 | 1 | 1 | 01/09/2026 | 01/13/2026 | 4 | 2 | Delayed | 2 |  |  | No
Sample Lobby Refresh | LOB-030 | Install temporary protection | detail | 2 | No | Yes | Eligible | 01/10/2026 | 01/13/2026 | 3 | 1 | 01/12/2026 | 01/14/2026 | 2 | 2 | Delayed | 3FS |  |  | No
Sample Lobby Refresh | LOB-040 | Remove existing finishes | detail | 2 | No | Yes | Eligible | 01/13/2026 | 01/14/2026 | 1 | 1 | 01/17/2026 | 01/16/2026 | -1 | 0 | Mixed Movement | 4FS+2d |  |  | No
Sample Lobby Refresh | LOB-050 | Wall prep and paint | detail | 2 | No | Yes | Eligible | 01/18/2026 | 01/17/2026 | -1 | 1 | 01/22/2026 | 01/22/2026 | 0 | 0 | Start Accelerated / Finish Unchanged | 5SS |  |  | No
Sample Lobby Refresh | LOB-060 | Lighting refresh package | likely-summary | 2 | Yes | No | Parent/summary row based on hierarchy | 01/23/2026 | 01/24/2026 | 1 | 0 | 01/28/2026 | 01/30/2026 | 2 | 2 | Delayed |  |  |  | Yes
Sample Lobby Refresh | LOB-070 | Remove old fixtures | detail | 3 | No | Yes | Eligible | 01/23/2026 | 01/24/2026 | 1 | 0 | 01/24/2026 | 01/25/2026 | 1 | -1 | Delayed | 6FS |  |  | No
Sample Lobby Refresh | LOB-080 | Install new fixtures | detail | 3 | No | Yes | Eligible | 01/25/2026 | 01/24/2026 | -1 | 1 | 01/27/2026 | 01/26/2026 | -1 | -1 | Accelerated | 8FS |  |  | No
Sample Lobby Refresh | LOB-090 | Final walkthrough | detail | 2 | No | Yes | Eligible | 01/28/2026 | 01/29/2026 | 1 | 1 | 01/29/2026 | 01/30/2026 | 1 | 1 | Delayed | 9FS |  |  | No
Sample Pool Repairs | POOL-000 | Sample Pool Repairs Summary | likely-summary | 1 | Yes | No | Parent/summary row based on hierarchy | 02/02/2026 | 02/02/2026 | 0 | 0 | 02/17/2026 | 02/18/2026 | 1 | 1 | Delayed |  |  |  | Yes
Sample Pool Repairs | POOL-010 | Scope confirmation | detail | 2 | No | Yes | Eligible | 02/02/2026 | 02/02/2026 | 0 | 0 | 02/02/2026 | 02/02/2026 | 0 | 0 | Unchanged |  |  |  | No
Sample Pool Repairs | POOL-020 | Drain and clean pool | detail | 2 | No | Yes | Eligible | 02/03/2026 | 02/03/2026 | 0 | 0 | 02/04/2026 | 02/05/2026 | 1 | 1 | Delayed | 12 |  |  | No
Sample Pool Repairs | POOL-030 | Surface inspection | detail | 2 | No | Yes | Eligible | 02/05/2026 | 02/06/2026 | 1 | 1 | 02/05/2026 | 02/06/2026 | 1 | 1 | Delayed | 13FS |  |  | No
Sample Pool Repairs | POOL-040 | Crack repair prep | detail | 2 | No | Yes | Eligible | 02/06/2026 | 02/07/2026 | 1 | 0 | 02/08/2026 | 02/08/2026 | 0 | 0 | Start Delayed / Finish Unchanged | 14FS+2d |  |  | No
Sample Pool Repairs | POOL-050 | Tile repair package | likely-summary | 2 | Yes | No | Parent/summary row based on hierarchy | 02/09/2026 | 02/08/2026 | -1 | 0 | 02/14/2026 | 02/14/2026 | 0 | 0 | Start Accelerated / Finish Unchanged |  |  |  | Yes
Sample Pool Repairs | POOL-060 | Remove damaged tile | detail | 3 | No | Yes | Eligible | 02/09/2026 | 02/08/2026 | -1 | 0 | 02/10/2026 | 02/09/2026 | -1 | -1 | Accelerated | 15SS |  |  | No
Sample Pool Repairs | POOL-070 | Install replacement tile | detail | 3 | No | Yes | Eligible | 02/11/2026 | 02/12/2026 | 1 | 1 | 02/13/2026 | 02/14/2026 | 1 | 0 | Delayed | 17FS |  |  | No
Sample Pool Repairs | POOL-080 | Deck coating touch-up | detail | 2 | No | Yes | Eligible | 02/14/2026 | 02/13/2026 | -1 | 0 | 02/16/2026 | 02/17/2026 | 1 | 1 | Mixed Movement | 18FS |  |  | No
Sample Pool Repairs | POOL-090 | Final inspection | detail | 2 | No | Yes | Eligible | 02/17/2026 | 02/18/2026 | 1 | 1 | 02/17/2026 | 02/18/2026 | 1 | 1 | Delayed | 19FS |  |  | No

## Warnings - Data Quality
Project Name | Task ID | Task / Milestone | Row Classification | Hierarchy Level | Has Child Rows | Critical Path Eligible | Critical Path Exclusion Reason | Baseline Start | Baseline Finish | Current Start | Current Finish | Movement Status | Warnings | Excluded From Movement Calculations | Excluded From Future Critical Path

## Dependency Validation
Source Row Number | Excel Row Number | Task ID | Task / Milestone | Row Classification | Predecessor Value | Parsed Reference | Relationship Type | Lag Days | Resolved? | Resolved Task ID | Resolved Task / Milestone | Issue / Warning

## Estimated Critical Path
Project Name | Path Type | Sequence | Task ID | Task / Milestone | Row Classification | Hierarchy Level | Has Child Rows | Critical Path Eligible | Critical Path Exclusion Reason | Baseline Start | Baseline Finish | Current Start | Current Finish | Finish Calendar Movement | Finish Workday Movement | Movement Status | Critical Path Status | Baseline Critical Path Sequence | Current Critical Path Sequence | Predecessors | Excluded From Future Critical Path
Sample Lobby Refresh | Baseline | 1 | LOB-010 | Kickoff and site review | detail | 2 | No | Yes | Eligible | 01/06/2026 | 01/06/2026 | 01/06/2026 | 01/06/2026 | 0 | 0 | Unchanged | Both | 1 | 1 |  | No
Sample Lobby Refresh | Baseline | 2 | LOB-020 | Order finish materials | detail | 2 | No | Yes | Eligible | 01/07/2026 | 01/09/2026 | 01/08/2026 | 01/13/2026 | 4 | 2 | Delayed | Both | 2 | 2 | 2 | No
Sample Lobby Refresh | Baseline | 3 | LOB-030 | Install temporary protection | detail | 2 | No | Yes | Eligible | 01/10/2026 | 01/12/2026 | 01/13/2026 | 01/14/2026 | 2 | 2 | Delayed | Both | 3 | 3 | 3FS | No
Sample Lobby Refresh | Baseline | 4 | LOB-040 | Remove existing finishes | detail | 2 | No | Yes | Eligible | 01/13/2026 | 01/17/2026 | 01/14/2026 | 01/16/2026 | -1 | 0 | Mixed Movement | Both | 4 | 4 | 4FS+2d | No
Sample Lobby Refresh | Baseline | 5 | LOB-050 | Wall prep and paint | detail | 2 | No | Yes | Eligible | 01/18/2026 | 01/22/2026 | 01/17/2026 | 01/22/2026 | 0 | 0 | Start Accelerated / Finish Unchanged | Both | 5 | 5 | 5SS | No
Sample Lobby Refresh | Baseline | 6 | LOB-070 | Remove old fixtures | detail | 3 | No | Yes | Eligible | 01/23/2026 | 01/24/2026 | 01/24/2026 | 01/25/2026 | 1 | -1 | Delayed | Both | 6 | 6 | 6FS | No
Sample Lobby Refresh | Baseline | 7 | LOB-080 | Install new fixtures | detail | 3 | No | Yes | Eligible | 01/25/2026 | 01/27/2026 | 01/24/2026 | 01/26/2026 | -1 | -1 | Accelerated | Both | 7 | 7 | 8FS | No
Sample Lobby Refresh | Baseline | 8 | LOB-090 | Final walkthrough | detail | 2 | No | Yes | Eligible | 01/28/2026 | 01/29/2026 | 01/29/2026 | 01/30/2026 | 1 | 1 | Delayed | Both | 8 | 8 | 9FS | No
Sample Lobby Refresh | Current | 1 | LOB-010 | Kickoff and site review | detail | 2 | No | Yes | Eligible | 01/06/2026 | 01/06/2026 | 01/06/2026 | 01/06/2026 | 0 | 0 | Unchanged | Both | 1 | 1 |  | No
Sample Lobby Refresh | Current | 2 | LOB-020 | Order finish materials | detail | 2 | No | Yes | Eligible | 01/07/2026 | 01/09/2026 | 01/08/2026 | 01/13/2026 | 4 | 2 | Delayed | Both | 2 | 2 | 2 | No
Sample Lobby Refresh | Current | 3 | LOB-030 | Install temporary protection | detail | 2 | No | Yes | Eligible | 01/10/2026 | 01/12/2026 | 01/13/2026 | 01/14/2026 | 2 | 2 | Delayed | Both | 3 | 3 | 3FS | No
Sample Lobby Refresh | Current | 4 | LOB-040 | Remove existing finishes | detail | 2 | No | Yes | Eligible | 01/13/2026 | 01/17/2026 | 01/14/2026 | 01/16/2026 | -1 | 0 | Mixed Movement | Both | 4 | 4 | 4FS+2d | No
Sample Lobby Refresh | Current | 5 | LOB-050 | Wall prep and paint | detail | 2 | No | Yes | Eligible | 01/18/2026 | 01/22/2026 | 01/17/2026 | 01/22/2026 | 0 | 0 | Start Accelerated / Finish Unchanged | Both | 5 | 5 | 5SS | No
Sample Lobby Refresh | Current | 6 | LOB-070 | Remove old fixtures | detail | 3 | No | Yes | Eligible | 01/23/2026 | 01/24/2026 | 01/24/2026 | 01/25/2026 | 1 | -1 | Delayed | Both | 6 | 6 | 6FS | No
Sample Lobby Refresh | Current | 7 | LOB-080 | Install new fixtures | detail | 3 | No | Yes | Eligible | 01/25/2026 | 01/27/2026 | 01/24/2026 | 01/26/2026 | -1 | -1 | Accelerated | Both | 7 | 7 | 8FS | No
Sample Lobby Refresh | Current | 8 | LOB-090 | Final walkthrough | detail | 2 | No | Yes | Eligible | 01/28/2026 | 01/29/2026 | 01/29/2026 | 01/30/2026 | 1 | 1 | Delayed | Both | 8 | 8 | 9FS | No
Sample Pool Repairs | Baseline | 1 | POOL-010 | Scope confirmation | detail | 2 | No | Yes | Eligible | 02/02/2026 | 02/02/2026 | 02/02/2026 | 02/02/2026 | 0 | 0 | Unchanged | Both | 1 | 1 |  | No
Sample Pool Repairs | Baseline | 2 | POOL-020 | Drain and clean pool | detail | 2 | No | Yes | Eligible | 02/03/2026 | 02/04/2026 | 02/03/2026 | 02/05/2026 | 1 | 1 | Delayed | Both | 2 | 2 | 12 | No
Sample Pool Repairs | Baseline | 3 | POOL-030 | Surface inspection | detail | 2 | No | Yes | Eligible | 02/05/2026 | 02/05/2026 | 02/06/2026 | 02/06/2026 | 1 | 1 | Delayed | Both | 3 | 3 | 13FS | No
Sample Pool Repairs | Baseline | 4 | POOL-040 | Crack repair prep | detail | 2 | No | Yes | Eligible | 02/06/2026 | 02/08/2026 | 02/07/2026 | 02/08/2026 | 0 | 0 | Start Delayed / Finish Unchanged | Both | 4 | 4 | 14FS+2d | No
Sample Pool Repairs | Baseline | 5 | POOL-060 | Remove damaged tile | detail | 3 | No | Yes | Eligible | 02/09/2026 | 02/10/2026 | 02/08/2026 | 02/09/2026 | -1 | -1 | Accelerated | Both | 5 | 5 | 15SS | No
Sample Pool Repairs | Baseline | 6 | POOL-070 | Install replacement tile | detail | 3 | No | Yes | Eligible | 02/11/2026 | 02/13/2026 | 02/12/2026 | 02/14/2026 | 1 | 0 | Delayed | Both | 6 | 6 | 17FS | No
Sample Pool Repairs | Baseline | 7 | POOL-080 | Deck coating touch-up | detail | 2 | No | Yes | Eligible | 02/14/2026 | 02/16/2026 | 02/13/2026 | 02/17/2026 | 1 | 1 | Mixed Movement | Both | 7 | 7 | 18FS | No
Sample Pool Repairs | Baseline | 8 | POOL-090 | Final inspection | detail | 2 | No | Yes | Eligible | 02/17/2026 | 02/17/2026 | 02/18/2026 | 02/18/2026 | 1 | 1 | Delayed | Both | 8 | 8 | 19FS | No
Sample Pool Repairs | Current | 1 | POOL-010 | Scope confirmation | detail | 2 | No | Yes | Eligible | 02/02/2026 | 02/02/2026 | 02/02/2026 | 02/02/2026 | 0 | 0 | Unchanged | Both | 1 | 1 |  | No
Sample Pool Repairs | Current | 2 | POOL-020 | Drain and clean pool | detail | 2 | No | Yes | Eligible | 02/03/2026 | 02/04/2026 | 02/03/2026 | 02/05/2026 | 1 | 1 | Delayed | Both | 2 | 2 | 12 | No
Sample Pool Repairs | Current | 3 | POOL-030 | Surface inspection | detail | 2 | No | Yes | Eligible | 02/05/2026 | 02/05/2026 | 02/06/2026 | 02/06/2026 | 1 | 1 | Delayed | Both | 3 | 3 | 13FS | No
Sample Pool Repairs | Current | 4 | POOL-040 | Crack repair prep | detail | 2 | No | Yes | Eligible | 02/06/2026 | 02/08/2026 | 02/07/2026 | 02/08/2026 | 0 | 0 | Start Delayed / Finish Unchanged | Both | 4 | 4 | 14FS+2d | No
Sample Pool Repairs | Current | 5 | POOL-060 | Remove damaged tile | detail | 3 | No | Yes | Eligible | 02/09/2026 | 02/10/2026 | 02/08/2026 | 02/09/2026 | -1 | -1 | Accelerated | Both | 5 | 5 | 15SS | No
Sample Pool Repairs | Current | 6 | POOL-070 | Install replacement tile | detail | 3 | No | Yes | Eligible | 02/11/2026 | 02/13/2026 | 02/12/2026 | 02/14/2026 | 1 | 0 | Delayed | Both | 6 | 6 | 17FS | No
Sample Pool Repairs | Current | 7 | POOL-080 | Deck coating touch-up | detail | 2 | No | Yes | Eligible | 02/14/2026 | 02/16/2026 | 02/13/2026 | 02/17/2026 | 1 | 1 | Mixed Movement | Both | 7 | 7 | 18FS | No
Sample Pool Repairs | Current | 8 | POOL-090 | Final inspection | detail | 2 | No | Yes | Eligible | 02/17/2026 | 02/17/2026 | 02/18/2026 | 02/18/2026 | 1 | 1 | Delayed | Both | 8 | 8 | 19FS | No

## Column Mapping Used
Mapped Column Category | Workbook Column Name
Task ID / Row ID column | Task ID
Task or Milestone Name column | Task Name
Baseline Start column | Baseline Start
Baseline Finish column | Baseline Finish
Actual / Current Start column | Current Start
Actual / Current Finish column | Current Finish
Predecessors column | Predecessors
Row Hierarchy / Outline Level column | Hierarchy Level
Project Name / Project Grouping column | Project Name
Status / % Complete column